## Charter Comm Calendar of Action
Newburyport Charter Commission
Calendar of Action
November 2009 - November 2011
Commission Action |  | Start Date | End Date | Duration (days) | Duration (months) | Countdown to Preliminary Report | Countdown to Final Report | Countdown to Election
Final Report Due | Submit to City Council; send copies to AG and Exec Office of Communities & Development | 2009-11-03 | 2011-05-03 | 540 | 18
Preliminary Report | Publish report in local newspaper; report to voters by request; copies of report to Attorney General and Exec Office of Comm & Devel | 2009-11-03 | 2011-03-03 | 480 | 16
Phase I - Organization |  | 2009-11-03 | 2010-01-06 | 63 | 2.1 | 480 | 540 | 725
Mandatory Public Hearing |  | 2009-11-03 | 2009-12-18 | 45 | 1.5
Commission Meeting | Swearing In | 2009-11-13 | 2009-11-13
Commission Meeting |  | 2009-11-18 | 2009-11-18
Commission Meeting |  | 2009-11-24 | 2009-11-24
Commission Meeting |  | 2009-12-02 | 2009-12-01
Commission Meeting |  | 2009-12-09 | 2009-12-09
1st Public Hearing |  | 2009-12-16 | 2009-12-16
Phase II - Research Committee Establishment | Mayor; Manager; Depts, Committees; Commissions | 2010-01-06 | 2010-04-17 | 101 | 3.3667 | 417 | 477 | 662
Commission Meeting |  | 2010-01-06 | 2010-01-06
Commission Meeting |  | 2010-01-20 | 2010-01-20
Commission Meeting |  | 2010-02-03 | 2010-02-03
2nd Public Hearing |  | 2010-02-24
Commission Meeting |  | 2010-03-03 | 2010-03-03
Phase III - Comparative Analysis; Additional Research | High level analysis of Basic Committee Research | 2010-04-07 | 2010-09-01 | 144 | 4.8 | 326 | 386 | 571
Commission Meeting |  | 2010-04-07 | 2010-04-07
Mayor / Manager
Research Executive; Legislative branches / Existing Charter
Commission Meeting |  | 2010-05-05 | 2010-05-05
3rd Public Hearing |  | 2010-05-19 | 2010-05-26
Commission Meeting |  | 2010-06-02 | 2010-06-02
Commission Meeting |  | 2010-07-07 | 2010-07-07
Commission Meeting |  | 2010-08-04 | 2010-08-04
Phase IV - Development of Rough Draft |  | 2010-09-01 | 2011-02-02 | 151 | 5.0333 | 182 | 242 | 427
Commission Meeting |  | 2010-09-01 | 2010-09-01
4th Public Hearing |  | 2010-09-22 | 2010-09-29
Commission Meeting |  | 2010-10-06 | 2010-10-06
Commission Meeting |  | 2010-11-03 | 2010-11-03
Commission Meeting |  | 2010-12-01 | 2010-12-01
Commission Meeting |  | 2011-01-05 | 2011-01-05
5th Public Hearing |  | 2011-01-19 | 2011-01-26
Phase V - Finalization of Preliminary Report |  | 2011-02-02 | 2011-03-03 | 31 |  | 31 | 91 | 276
Commission Meeting |  | 2011-02-16 | 2011-02-16
Commission Meeting |  | 2011-02-23 | 2011-02-23
Phase VI - Final Report |  | 2011-03-03 | 2011-05-03 | 60 | 2 |  | 60 | 245
AG's Legal Opinion |  | 2011-03-03 | 2011-03-31 | 28
Mandatory Public Hearing |  | 2011-03-03 | 2011-03-31 | 28
6th Public Hearing |  | 2011-03-16 | 2011-03-23
Phase VII - Road to Election Day |  | 2011-05-03 | 2011-11-08 | 185 | 6.1667 |  |  | 185
`